## Form 3
Annual Development Plan - 2022
Criteria Based Grants (CBG)
Ministry |  | Ministry of Agriculture,agrarian development,irrigation,water supply and drainage ,Food supply and distribution trade
Sector |  | Water Supply and Drainage
Toatal Budget for the sector Rs 15 Mn
S.No | Component and Budget (Rs Mn) | SDG Target No | Sub component and Budget (Rs.Mn) | Outcomes |  |  |  | Broad Activity Area | Output | Budget (Rs.Mn)
|  |  |  | KPIs | Baseline | Target
[5 empty] | 2021 | 2022 | 2023
1 | 1.Watershed Managemet Rs 0.15 Mn | Goal 6.6 | 1.1 Conservation and development of water resources and reserved areas Rs 0.15 Mn | coverd consevation areas (ha) | 10 | 15 | 15 | 1.1.1 Implementation of Tree planting Activities and fixing the botanical name Boards | Number of Planted Trees | 0.15
2 | 2.Ensuring the safe and continuous drinking water supply Rs 14.65Mn | Goal 6.1 & Goal 6.4 | 2.1 Construction and Development of Water Supply Schemes Rs 13.45Mn | No of benificiaries | 4010 | 5000 | 6000 | 2.1.1.Introducing new purification systems and Implementation /Renovation of community based water supply Systems | Number of community based water supply Systems | 4.2
|  |  |  | No of benificiaries | 1525 | 2000 | 3000 | 2.1.2 Establishment of Tube wells/Wells | Number of tube wells / wells | 3
|  |  |  | No of benificiaries | 1580 | 2000 | 2500 | 2.1.3 Extending water lines and supplying new water connections | Number of water lines | 6.45 | 13.65
|  |  | 2.2.Ensuaring safty and quality of drinking water RS 1.2 Mn | Number of safe water access CBO | 9 | 10 | 11 | 2.2.1 Supply of Water Meters for CBO | No of water meters | 0.9
|  |  |  | Number of safe water access CBO/Public places | 91 | 120 | 140 | 2.2.2 Testing of water Quality in Community water projects/Public places and conducting awareness programms | Number of tested samples and Number of awareness programms | 0.3 | 1.2
Total | [9 empty] | 15
[11 empty] | 15 | 0

## Form 3 A
Annual Development Plan - 2022
Criteria Based Grants (CBG)
Ministry | Ministry of Agriculture,agrarian development,irrigation,water supply and drainage ,Food supply and distribution trade
Sector | Water Supply and Drainage |  | Total Budget for the sector (Rs Mn.) |  |  | 15
Component 1 | Watershed Management |  | Total Budget for the component 1 (Rs Mn.) |  |  | 0.15
Sub Component and Budget (Rs) | Broad Activity Area and Budget (Rs Mn) | List of activity | Budget Rs Mn
|  |  | Total Estimated Cost (TEC) | Galle | Matara | Hambanthota
1.1 Conservation and development of water resources and reserved area - Rs 0.15 Mn | 1.1.1 Implementation of Tree planting Activities - Rs 0.15 Mn | 1.1.1.1 Planting the favourable plants like kumbuk,mee,Na in watershed areas and fixing the botnical name boards | 0.15 | 0.05 | 0.05 | 0.05
Sub Total |  |  | 0.15 | 0.05 | 0.05 | 0.05
Component 2 | Ensuring the safe and continuous drinking water supply |  | Total Budget for the component 1 (Rs Mn.) |  |  | 14.85
Sub Component and Budget (Rs) | Broad Activity Area and Budget (Rs) | List of activity | Budget Rs Mn
|  |  | Total Estimated Cost (TEC) | Galle | Matara | Hambanthota
2.1 Construction and Development of Water Supply Schemes Rs 13.65 Mn | 2.1.1.Introducing new purification systems and Implementation / Renovation of community based water supply Systems Rs 4.2 Mn | 2.1.1.1 Implementing drinking water supplyning project in selected schools | 3 | 1 | 1 | 1
|  | 2.1.1.2 Implementing Community base water supplying projects with the Department of community water supply and Divisional Secretariats offices | 1.2 | 0 | 0 | 1.2
| 2.1.2 Establishment Tube wells/Wells Rs 3Mn | 2.1.2.1 Establishment tube wells in public Places with NWSDB & relevant Divisional secretariat offices | 3 | 1 | 1 | 1
| 2.1.3 Extending water lines and supply new water connections Rs 6.45Mn | 2.1.3.1 Extending the water lines with National Water Supply and Drainage Board | 6.45 | 2.95 | 1.5 | 2
2.2 Ensuaring safty and quality of drinking water Rs 1.2 Mn | 2.2.1 Supply of Water Meters for CBO Rs 0.9 Mn | 2.2.1.1 Suppling of water meters for selected CBOs in Galle Matara and Hambantota Districts | 0.9 | 0.3 | 0.35 | 0.25
| 2.2.2 Testing of water Quality in Community water projects/Public places and conducting awareness programms Rs 0.3 Mn | 2.2.2.1 Testing of water quality in community water projects of public places and conducting awareness programms | 0.3 | 0.1 | 0.1 | 0.1
Sub Total |  |  | 14.85 | 5.35 | 3.95 | 5.55
Grand Total |  |  | 15 | 5.4 | 4 | 5.6
|  |  |  | 36% | 26.67% | 37.33%